## Sheet1
Task | Start Date | Days to complete
UC1 Log in to Application | 2017-09-30 | 16
1. Create login screen user/pw | 2017-09-30 | 2
2. Create authentication to server | 2017-10-02 | 14
UC2 Browse Customers | 2017-09-30 | 7
1. Create scrollable/clickable list of customers | 2017-09-30 | 7
UC3 View Customer Info | 2017-10-07 | 7
1. Display customer info | 2017-10-07 | 7
UC4 Add new customer | 2017-09-30 | 7
1. Create new customer button | 2017-09-30 | 7
2. Link button to customer info page | 2017-10-07 | 7
UC5 View project | 2017-10-14 | 6 | 7
1. Link clickable project to info | 2017-10-14 | 6
UC16 Add note | 2017-10-14 | 6
1. Add textbox for user to add note | 2017-10-14 | 6
2. Save note server end | 2017-10-14 | 6
UC25 Create new project | 2017-10-07 | 7
1. Create scrollable/clickable list of projects/quotes | 2017-10-07 | 7
2. Link project to show info | 2017-10-14 | 6
UC26 Create account | 2017-09-30 | 20
1. Create master account manually to approve other accounts | 2017-09-30 | 1
2. Create button to create account | 2017-09-30 | 1
3. Link button to create account page | 2017-09-30 | 7
4. Take info and authenticate password | 2017-10-07 | 13
5. Show account created screen | 2017-10-07 | 13
UC6 Modify project | 2017-10-20 | 7
1. Edit info with clicked | 2017-10-20 | 7
UC7 Add fence | 2017-10-20 | 14
1. Add fence to drawing | 2017-10-20 | 7
2. Server end estimate for fence | 2017-10-27 | 7
UC8 Remove fence | 2017-10-20 | 14
1. Remove fence from drawing | 2017-10-20 | 7
2. Server end estimate update | 2017-10-27 | 7
UC9 Modify fence | 2017-10-20 | 14
1. Change fence attributes | 2017-10-20 | 7
2. Server end estimate update | 2017-10-27 | 7
UC10 Add gate | 2017-10-20 | 14
1. Add gate to drawing | 2017-10-20 | 7
2. Server end estimate update | 2017-10-27 | 7
UC11 Remove gate | 2017-10-20 | 14
1. Remove gate to drawing | 2017-10-20 | 7
2. Server end estimate update | 2017-10-27 | 7
UC12 Modify gate | 2017-10-20 | 14
1. Modify gate attributes | 2017-10-20 | 7
2. Server end estimate update | 2017-10-27 | 7
UC13 Add a building | 2017-10-20 | 7
1. Add building icon to drawing house/garage | 2017-10-20 | 7
UC14 Remove bulding | 2017-10-20 | 7
2. Remove building icon from drawing house/garage | 2017-10-20 | 7
UC17 Change status | 2017-10-20 | 7
1. Give project new, inprogress, or complete status | 2017-10-20 | 7
2. Update the status in server | 2017-10-20 | 7
UC18 View project summary | 2017-11-04 | 6
1. Display all project info | 2017-11-04 | 6
UC19 Send email to customer and supplier | 2017-11-04 | 6
1. Create button for customer | 2017-11-04 | 6
2. Create button for supplier | 2017-11-04 | 6
3. Send email | 2017-11-04 | 6
UC24 Add project picture | 2017-11-04 | 6
1. Create button for option to take picture | 2017-11-04 | 6
2. Capture picture from camera and display on screen | 2017-11-04 | 6
UC15 Modify quote | 2017-11-10 | 7
1. Allow user to edit quote | 2017-11-10 | 2
2. Apply discounts on server end | 2017-11-12 | 5
UC20 View accounting summary | 2017-11-10 | 7
1. Create button to view accounting summary | 2017-11-10 | 1
2. View all accounting info | 2017-11-11 | 6
UC21 Export accounting summary | 2017-11-10 | 14
1. Create button to export accounting summary | 2017-11-10 | 1
2. Export into file type (excel) | 2017-11-11 | 13
UC22 View fencing attributes | 2017-11-17 | 7
1. Create button to view fencing attributes | 2017-11-17 | 1
2. Display in new page list of materials, colors, styles, cost | 2017-11-18 | 6
UC23 Import fencing attributes | 2017-11-10 | 20
1. Create button for import of excel files | 2017-11-11 | 1
2. Display | 2017-11-12 | 19
|  |  |  | UC15 Modify quote | 2017-11-10 | 7
|  |  |  | 1. Allow user to edit quote | 2017-11-10 | 2
|  |  |  | 2. Apply discounts on server end | 2017-11-12 | 5
|  |  |  | UC20 View accounting summary | 2017-11-10 | 7
|  |  |  | 1. Create button to view accounting summary | 2017-11-10 | 1
|  |  |  | 2. View all accounting info | 2017-11-11 | 6
|  |  |  | UC21 Export accounting summary | 2017-11-10 | 14
|  |  |  | 1. Create button to export accounting summary | 2017-11-10 | 1
|  |  |  | 2. Export into file type (excel) | 2017-11-11 | 13
|  |  |  | UC22 View fencing attributes | 2017-11-17 | 7
|  |  |  | 1. Create button to view fencing attributes | 2017-11-17 | 1
|  |  |  | 2. Display in new page list of materials, colors, styles, cost | 2017-11-18 | 6
|  |  |  | UC23 Import fencing attributes | 2017-11-10 | 20
|  |  |  | 1. Create button for import of excel files | 2017-11-11 | 1
|  |  |  | 2. Display | 2017-11-12 | 19