## Sheet1
Task | Start Date | Days to complete
UC1 Log in to Application | 2017-09-30 | 16
1. Create login screen user/pw | 2017-09-30 | 2
2. Create authentication to server | 2017-10-02 | 14
UC2 Browse Customers | 2017-09-30 | 7
1. Create scrollable/clickable list of customers | 2017-09-30 | 7
UC3 View Customer Info | 2017-10-07 | 7
1. Display customer info | 2017-10-07 | 7
UC4 Add new customer | 2017-09-30 | 7
1. Create new customer button | 2017-09-30 | 7
2. Link button to customer info page | 2017-10-07 | 7
UC5 View project |  | 20
1. Link clickable project to info |  | 20
UC16 Add note |  | 20
1. Add textbox for user to add note |  | 20
2. Save note server end |  | 20
UC25 Create new project |  | 20
1. Create scrollable/clickable list of projects/quotes |  | 20
2. Link project to show info |  | 20
UC26 Create account |  | 20
1. Create master account manually to approve other accounts |  | 20
2. Create button to create account |  | 20
3. Link button to create account page |  | 20
4. Take info and authenticate password |  | 20
5. Show account created screen |  | 20
UC6 Modify project |  | 20
UC7 Add fence |  | 20
UC8 Remove fence |  | 20
UC9 Modify fence |  | 20
UC10 Add gate
UC11 Remove gate
UC12 Modify gate
UC13 Add a building
UC14 Remove bulding
UC17 Change status
UC18 View project summary
UC19 Send email to customer and supplier
UC24 Add project picture
UC15 Modify quote
UC20 View accounting summary
UC21 Export accounting summary
UC22 View fencing attributes
UC23 Import fencing attributes